## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
Home Page | Public | Complex | Iteration 1 | HE153046 | Nguyen The Giang(BE-50, FE-50) | Iteration 1
Products List | Public | Complex | Iteration 1 | HE153046, HE150346 | Nguyen The Giang(BE-50), Bui Ngoc Huyen(FE-50) | Iteration 1
Product Details | Public | Simple | Iteration 1 | HE153046 | Nguyen The Giang(BE-50, FE-50) | Iteration 1
Cart Details | Public | Medium | Iteration 1 | HE153046, HE150346 | Nguyen The Giang(BE-70), Bui Ngoc Huyen(FE-30) | Iteration 1
User Login | Common | Complex | Iteration 1 | HE153046, HE150346, HE153590, HE150411 | Nguyen The Giang(BE-20), Bui Ngoc Huyen(FE-40), Dinh The Thuan(BE-20), Tran Tat Dat(BE-20) | Iteration 1
User Register | Common | Complex | Iteration 1 | HE153046, HE150346, HE153590, HE150411 | Nguyen The Giang(BE-20), Bui Ngoc Huyen(FE-40), Dinh The Thuan(BE-20), Tran Tat Dat(BE-20) | Iteration 1
User Authorization | Common | Simple | Iteration 1 | HE150340 | Phung Quang Thong(BE-50, FE-50) | Iteration 1
Admin Dashboard | Admin | Complex | Iteration 1 | HE153046, HE150346, HE153590 | Nguyen The Giang(BE-30), Bui Ngoc Huyen(FE-40, BE-20), Dinh The Thuan(BE-10) | Iteration 1
Users List | Admin | Medium | Iteration 1 | HE153046, HE150340 | Nguyen The Giang(BE-50), Phung Quang Thong(BE-50) | Iteration 1
Cart Completion (Place Order) | Public | Complex | Iteration 2 | HE153046, HE150346, HE150411, HE153590 | Nguyen The Giang(BE-25), Bui Ngoc Huyen(FE-25), Tran Tat Dat(BE-25), Dinh The Thuan(BE-25) | Iteration 2
Reset Password | Common | Complex | Iteration 2 | HE153046, HE150346 | Nguyen The Giang(BE-50), Bui Ngoc Huyen(FE-50) | Iteration 2
Change Password | Common | Medium | Iteration 2 | HE150411, HE150346 | Tran Tat Dat(BE-50), Bui Ngoc Huyen(FE-50) | Iteration 2
User Profile | Common | Medium | Iteration 2 | HE150411, HE150346 | Tran Tat Dat(BE-50), Bui Ngoc Huyen(FE-50) | Iteration 2
My Orders (xem lịch sử order) (tổng quát) | Customer | Medium | Iteration 2 | HE153590 | Dinh The Thuan(BE-50, FE-50) | Iteration 2
Order Information (chi tiết) | Customer | Medium | Iteration 2 | HE150411, HE153590 | Tran Tat Dat(BE,FE-50), Dinh The Thuan(BE,FE-50) | Iteration 2
Products List | Marketing | Medium | Iteration 2 | HE153046 | Nguyen The Giang(BE-50, FE-50) | Iteration 2
Customers List | Marketing | Medium | Iteration 2 | HE153590 | Dinh The Thuan(BE-50, FE-50) | Iteration 2
Customer Details | Marketing | Simple | Iteration 2 | HE153590 | Dinh The Thuan(BE-50, FE-50) | Iteration 2
Sale Dashboard | Marketing | Medium | Iteration 2 | HE153046, HE150346 | Nguyen The Giang(BE-50), Bui Ngoc Huyen(FE-50) | Iteration 2
Orders List | Admin | Medium | Iteration 2 | HE153590 | Dinh The Thuan(BE-50, FE-50) | Iteration 2
Order Details | Marketing | Medium | Iteration 2 | HE153590 | Dinh The Thuan(BE-50, FE-50) | Iteration 2
Feedback | Public | Complex | Iteration 2 | HE150411, HE150340,HE150346 | Tran Tat Dat(BE-70), Phung Quang Thong(BE-20),Bui Ngoc Huyen(FE-10) | Iteration 2
Blogs List | Public | Medium | Iteration 3 | HE150340 | Phung Quang Thong(BE-50, FE-50) | Iteration 3
Blog Details | Public | Simple | Iteration 3 | HE150340 | Phung Quang Thong(BE-50, FE-50) | Iteration 3
Posts List | Marketing | Simple | Iteration 3 | HE150340 | Phung Quang Thong(BE-50, FE-50) | Iteration 3
Post Details | Marketing | Simple | Iteration 3 | HE150340 | Phung Quang Thong(BE-50, FE-50) | Iteration 3
Feedbacks List | Marketing | Simple | Iteration 3 | HE150411 | Tran Tat Dat(BE-50, FE-50) | Iteration 3
Feedback Details | Marketing | Simple | Iteration 3 | HE150411 | Tran Tat Dat(BE-50, FE-50) | Iteration 3
Notification | Common | Simple | Iteration 3 | HE153590 | Dinh The Thuan(BE-50, FE-50) | Iteration 3
Compare Product | Public | Medium | Iteration 3 | HE153590 | Dinh The Thuan(BE-50, FE-50) | Iteration 3
Note:
BE: Back-end
FE: Front-end