## Wx
PROJECT REPORT
Group | Thunderbolt
Week | 12/07/2021-18/07/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Design Document | In Progress
2 | SRS Document | Completed
3 | Product Backlog | In Progress
4 | Coding Convention | Completed
5 | Database | In Progress
6 | Java Project | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | SRS Document | Whole Team
2 | Design Document | Whole Team
3 | Finish Feedback Feature | DatTT, HuyenBN
4 | Finish Blog Feature | ThongQP, HuyenBN
5 | Finish Compare Feature | ThuanDT
6 | Home Page | GiangNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Design Document | 19/07/2021 | Whole Team
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C24: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue