## Wx
PROJECT REPORT
Group | Thunderbolt
Week | 10/05/2021-16/05/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | SRS Document | Completed
2 | Web Skeleton | Completed
3 | Design Database | In Progress
4 | Design Document | In Progress
5 | Product Backlog | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | SRS Document | DatTT
2 | Web Skeleton | HuyenBN
3 | Design Document | GiangNT
4 | Design Database | ThongPQ
5 | Design Database | ThuanDT
6 | Product Backlog | GiangNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Database Completion | 23/5/2021
2 | Web Design Completion | 23/5/2021
3 | Work Division | 19/5/2021
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Group Meeting Using Discord | DatTT
2 | Use GitHub | GiangNT
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C22: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue