## Wx
PROJECT REPORT
Group | Thunderbolt
Week | 21/06/2021-27/06/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Design Document | In Progress
2 | SRS Document | In Progress
3 | Product Backlog | In Progress
4 | Coding Convention | Completed
5 | Database | In Progress
6 | Java Project | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Finish Forget Password Feature | GiangNT
2 | SRS Document | GiangNT | Screen flow of Admin, Use Case Diagram
3 | Product Backlog | GiangNT | Work Division
4 | Update Paging Feature | GiangNT
5 | Update Compare Feature | GiangNT
6 | DAO | GiangNT | Fix Style Query and Add Test Case for each function
7 | Plus and Minus Product In Cart Feature | GiangNT
8 | Forgot Password Page | HuyenBN | Style
9 | Login Page | HuyenBN | Style
10 | User Profile Page | HuyenBN | Style
11 | Dashboard Page | HuyenBN | Style
12 | Add Address in Checkout Page | HuyenBN | Style
13 | Menu and Notification in Header Bar | HuyenBN | Style
14 | Place Order Feature | DatTT
15 | Send order detail by Email Feature | DatTT
16 | Update Checkout Feature | DatTT
17 | Feedback Feature | DatTT | Replies and Star
18 | Update Email Feature | DatTT
19 | SRS Document | ThuanDT | Screen flow of Seller, Screen Function Authorization
20 | View Order History Feature | ThuanDT
21 | Order Detail Feature | ThuanDT
22 | Invoice Feature | ThuanDT | Invoice List, Invoice Detail
23 | Order Feature | ThuanDT | Approve Order, Cancel Order
24 | Notification in Header Bar | ThuanDT
25 | Update JSP Page | ThongPQ | Style
26 | Controller Update | ThongPQ | Redirect Error
27 | Design Document | ThongPQ | Class Specifications of DAO, Controller
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Style Pages | 2021-04-07 | HuyenBN
2 | New Home Page Design | 2021-04-07 | GiangNT
3 | Update Web Skeleton | 2021-04-07 | GiangNT
4 | Blog Feature | 2021-04-07 | ThuanDT
5 | Update Feedback Feature | 2021-04-07 | DatTT
6 | Update Sequence Diagram | 2021-04-07 | ThongPQ
7 | Search Account in Manager Feature | 2021-04-07 | ThongPQ
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C45: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue