## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
Home Page | Public | Complex | Iteration 1
Products List | Public | Medium | Iteration 1
Product Details | Public | Medium | Iteration 1
Cart Details | Public | Medium | Iteration 1
Cart Contact (List Cart) | Public | Simple | Iteration 1
User Login | Common | Simple | Iteration 1
User Register | Common | Simple | Iteration 1
User Authorization (gửi mail) | Common | Simple | Iteration 1
Admin Dashboard | Admin | Simple | Iteration 1
Users List | Admin | Simple | Iteration 1
User Details | Admin | Simple | Iteration 1
Settings List | Admin | Simple | Iteration 1
Setting Details | Admin | Simple | Iteration 1
Cart Completion | Public | Simple | Iteration 2
Reset Password | Common | Simple | Iteration 2
Change Password | Common | Simple | Iteration 2
User Profile | Common | Simple | Iteration 2
My Orders (xem lịch sử order) (tổng quát) | Customer | Simple | Iteration 2
Order Information (chi tiết) | Customer | Simple | Iteration 2
Products List | Marketing | Simple | Iteration 2
Product Details | Marketing | Simple | Iteration 2
Customers List | Marketing | Simple | Iteration 2
Customer Details | Marketing | Simple | Iteration 2
Sale Dashboard | Sale | Simple | Iteration 2
Orders List | Sale | Simple | Iteration 2
Order Details | Sale | Simple | Iteration 2
Feedback | Public | Simple | Iteration 2
Blogs List | Public | Simple | Iteration 3
Blog Details | Public | Simple | Iteration 3
MKT Dashboard | Marketing | Simple | Iteration 3
Posts List | Marketing | Simple | Iteration 3
Post Details | Marketing | Simple | Iteration 3
Sliders List | Marketing | Simple | Iteration 3
Slider Details | Marketing | Simple | Iteration 3
Feedbacks List | Marketing | Simple | Iteration 3
Feedback Details | Marketing | Simple | Iteration 3