## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration | Status | Detail
Home Page | Public | Complex | Iteration 1 |  |  |  | Đang
Products List | Public | Complex | Iteration 1 | HE153046, HE150346 | Nguyen The Giang, Bui Ngoc Huyen
Product Details | Public | Medium | Iteration 1 | HE153046 | Nguyen The Giang |  | Còn feedback
Cart Details | Public | Medium | Iteration 1 | HE153046, HE150346 | Nguyen The Giang, Bui Ngoc Huyen
Cart Contact (List Cart) | Public | Simple | Iteration 1 | HE153046, HE150346 | Nguyen The Giang, Bui Ngoc Huyen
User Login | Common | Simple | Iteration 1 | HE153046, HE150346 | Nguyen The Giang, Bui Ngoc Huyen
User Register | Common | Medium | Iteration 1 | HE153046, HE150346 | Nguyen The Giang, Bui Ngoc Huyen
User Authorization | Common | Medium | Iteration 1 | HE150411, HE150346 | Tran Tat Dat, Bui Ngoc Huyen
Admin Dashboard | Admin | Medium | Iteration 1 | HE153046, HE150346 | Nguyen The Giang, Bui Ngoc Huyen |  | Còn Style
Users List | Admin | Simple | Iteration 1 | HE153046, HE150340 | Nguyen The Giang, Phung Quang Thong |  | Còn Paging
User Details | Admin | Simple | Iteration 1 |  |  |  |  | Khi bấm vào 1 User trong List -> hiển thị chi tiết
Cart Completion (Place Order) | Public | Medium | Iteration 2 | HE153046, HE150346 | Nguyen The Giang, Bui Ngoc Huyen, Tran Tat Dat
Reset Password | Common | Complex | Iteration 2 | HE153046, HE150346 | Nguyen The Giang, Bui Ngoc Huyen
Change Password | Common | Simple | Iteration 2 | HE150411, HE150346 | Tran Tat Dat, Bui Ngoc Huyen
User Profile | Common | Simple | Iteration 2 | HE150411, HE150346 | Tran Tat Dat, Bui Ngoc Huyen |  | Còn Style
My Orders (xem lịch sử order) (tổng quát) | Customer | Simple | Iteration 2 | HE153590 | Dinh The Thuan |  | Còn Style
Order Information (chi tiết) | Customer | Simple | Iteration 2 | HE150411, HE153590 | Tran Tat Dat, Dinh The Thuan |  | Còn Style
Products List | Marketing | Simple | Iteration 2 | HE153046 | Nguyen The Giang |  |  | (Là Manager Product)
Product Details | Marketing | Simple | Iteration 2 |  |  |  |  | Khi bấm vào thì hiển thị Product Detail như User
Customers List | Marketing | Simple | Iteration 2 | HE153590 | Dinh The Thuan |  | Hỏi Thuận: Total Invoices có chưa (nếu chưa có thì thêm 1 trang nữa)
Customer Details | Marketing | Simple | Iteration 2 | HE153590 | Dinh The Thuan |  | cx thế
Sale Dashboard | Marketing | Medium | Iteration 2 | HE153046, HE150346 | Nguyen The Giang, Bui Ngoc Huyen
Orders List | Marketing | Simple | Iteration 2 | HE153590 | Dinh The Thuan |  | Sửa lại trang Total Invoices
Order Details | Marketing | Simple | Iteration 2 | HE153590 | Dinh The Thuan |  | Cx thế
Feedback | Public | Medium | Iteration 2 | HE150411, HE150340 | Tran Tat Dat, Phung Quang Thong
Blogs List | Public | Simple | Iteration 3 |  |  |  |  | Chỉ có Seller Post thôi
Blog Details | Public | Simple | Iteration 3
MKT Dashboard | Marketing | Simple | Iteration 3
Posts List | Marketing | Simple | Iteration 3 |  |  |  |  | Danh sách các Blog do Seller tạo ra
Post Details | Marketing | Simple | Iteration 3
Sliders List | Marketing | Simple | Iteration 3
Slider Details | Marketing | Simple | Iteration 3
Feedbacks List | Marketing | Simple | Iteration 3
Feedback Details | Marketing | Simple | Iteration 3