## Wx
PROJECT REPORT
Group | Thunderbolt
Week | 24/05/2021-30/05/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Sign in & Sign up Page Implementation | Completed
2 | Design Database | In Progress
3 | Send Verification Email for Sign up | Completed
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Sign in & Sign up Page Implementation | HuyenBN | Front-end Styling with CSS
2 | Design Database | GiangNT | General Design
3 | Design Database | ThuanDT | Insert Data Point
4 | Design Database | ThongPQ | Insert Data Point
5 | Send Verification Email for Sign up | DatTT | Java Coding
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Database Completion | 2021-06-06
2 | Send Verification Email for Reset Password | 2021-06-06
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C19: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue