## Wx
PROJECT REPORT
Group | Thunderbolt
Week | 14/06/2021-20/06/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Design Document | In Progress
2 | SRS Document | In Progress
3 | Product Backlog | In Progress
4 | Coding Convention | Completed
5 | Database | In Progress
6 | Java Project | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Java Coding Convention Document | GiangNT
2 | Manufacturer Feature | GiangNT
3 | Account Status Feature | DatTT
4 | Comment Code | ThongPQ
5 | Standardize Query Style | GiangNT | And add Test Case for DB Query
6 | Error Page Desgin | HuyenBN | Using CSS
7 | Order Feature: Add Tables to DB | DatTT | 3 Tables: Orders, Order_Detail, Order_Status
8 | Order Feature: Query in Java Project | ThuanDT | OrderDAO, OrderDetailDAO and other Entities
9 | Ship Information and User Address Feature | DatTT | DB Tables, DAO and Entities
10 | Update all Servlet | ThongPQ | Add try catch
11 | Change Password Page Design | HuyenBN | Using CSS
12 | Home Page and Menu Navbar Design | HuyenBN | Using CSS
13 | Invoice Feature | ThuanDT | Entity, DAO
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Forget Password Feature | 27/6/2021
2 | Update Documents | 27/6/2021
3 | Database Desgin | 27/6/2021
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C31: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue