## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration | Status | Detail
Home Page | Public | Complex | Iteration 1 | HE153046 | Nguyen The Giang(BE-50, FE-50)
Products List | Public | Complex | Iteration 1 | HE153046, HE150346 | Nguyen The Giang(BE-50), Bui Ngoc Huyen(FE-50)
Product Details | Public | Simple | Iteration 1 | HE153046 | Nguyen The Giang(BE-50, FE-50) |  | Còn feedback
Cart Details | Public | Medium | Iteration 1 | HE153046, HE150346 | Nguyen The Giang(BE-70), Bui Ngoc Huyen(FE-30)
User Login | Common | Complex | Iteration 1 | HE153046, HE150346, HE153590, HE150411 | Nguyen The Giang(BE-20), Bui Ngoc Huyen(FE-40), Dinh The Thuan(BE-20), Tran Tat Dat(BE-20)
User Register | Common | Complex | Iteration 1 | HE153046, HE150346, HE153590, HE150411 | Nguyen The Giang(BE-20), Bui Ngoc Huyen(FE-40), Dinh The Thuan(BE-20), Tran Tat Dat(BE-20)
User Authorization | Common | Simple | Iteration 1 | HE150340 | Phung Quang Thong(BE-50, FE-50)
Admin Dashboard | Admin | Complex | Iteration 1 | HE153046, HE150346, HE153590 | Nguyen The Giang(BE-30), Bui Ngoc Huyen(FE-40, BE-20), Dinh The Thuan(BE-10) |  | Còn Style | Đã xóa trong SRS (vì nó ko tồn tại)
Users List | Admin | Medium | Iteration 1 | HE153046, HE150340 | Nguyen The Giang(BE-50), Phung Quang Thong(BE-50) |  | Còn Paging
User Details | Admin | Simple | Iteration 1 |  |  |  |  | Khi bấm vào 1 User trong List -> hiển thị chi tiết
Cart Completion (Place Order) | Public | Complex | Iteration 2 | HE153046, HE150346, HE150411, HE153590 | Nguyen The Giang(BE-25), Bui Ngoc Huyen(FE-25), Tran Tat Dat(BE-25), Dinh The Thuan(BE-25)
Reset Password | Common | Complex | Iteration 2 | HE153046, HE150346 | Nguyen The Giang(BE-50), Bui Ngoc Huyen(FE-50)
Change Password | Common | Medium | Iteration 2 | HE150411, HE150346 | Tran Tat Dat(BE-50), Bui Ngoc Huyen(FE-50)
User Profile | Common | Medium | Iteration 2 | HE150411, HE150346 | Tran Tat Dat(BE-50), Bui Ngoc Huyen(FE-50) |  | Còn Style
My Orders (xem lịch sử order) (tổng quát) | Customer | Medium | Iteration 2 | HE153590 | Dinh The Thuan(BE-50, FE-50) |  | Còn Style
Order Information (chi tiết) | Customer | Medium | Iteration 2 | HE150411, HE153590 | Tran Tat Dat(BE,FE-50), Dinh The Thuan(BE,FE-50) |  | Còn Style
Products List | Marketing | Medium | Iteration 2 | HE153046 | Nguyen The Giang(BE-50, FE-50) |  |  | (Là Manager Product)
Product Details | Marketing | Simple | Iteration 2 |  |  |  |  | Khi bấm vào thì hiển thị Product Detail như User
Customers List | Marketing | Medium | Iteration 2 | HE153590 | Dinh The Thuan(BE-50, FE-50) |  | Hỏi Thuận: Total Invoices có chưa (nếu chưa có thì thêm 1 trang nữa)
Customer Details | Marketing | Simple | Iteration 2 | HE153590 | Dinh The Thuan(BE-50, FE-50) |  | cx thế
Sale Dashboard | Marketing | Medium | Iteration 2 | HE153046, HE150346 | Nguyen The Giang(BE-50), Bui Ngoc Huyen(FE-50)
Orders List | Admin | Medium | Iteration 2 | HE153590 | Dinh The Thuan(BE-50, FE-50) |  | Sửa lại trang Total Invoices
Order Details | Marketing | Medium | Iteration 2 | HE153590 | Dinh The Thuan(BE-50, FE-50) |  | Cx thế
Feedback | Public | Complex | Iteration 2 | HE150411, HE150340,HE150346 | Tran Tat Dat(BE-70), Phung Quang Thong(BE-20),Bui Ngoc Huyen(FE-10)
Blogs List | Public | Medium | Iteration 3 | HE150340 | Phung Quang Thong(BE-50, FE-50)
Blog Details | Public | Simple | Iteration 3 | HE150340 | Phung Quang Thong(BE-50, FE-50)
MKT Dashboard | Marketing | Simple | Iteration 3
Posts List | Marketing | Simple | Iteration 3 | HE150340 | Phung Quang Thong(BE-50, FE-50)
Post Details | Marketing | Simple | Iteration 3 | HE150340 | Phung Quang Thong(BE-50, FE-50)
Sliders List | Marketing | Simple | Iteration 3
Slider Details | Marketing | Simple | Iteration 3
Feedbacks List | Marketing | Simple | Iteration 3 | HE150411 | Tran Tat Dat(BE-50, FE-50)
Feedback Details | Marketing | Simple | Iteration 3 | HE150411 | Tran Tat Dat(BE-50, FE-50)
Notification | Common | Simple | Iteration 3 | HE153590 | Dinh The Thuan(BE-50, FE-50)
Compare Product | Public | Medium | Iteration 3 | HE153590 | Dinh The Thuan(BE-50, FE-50)
Note:
BE: Back-end
FE: Front-end