## Wx
PROJECT REPORT
Group | Thunderbolt
Week | 28/06/2021-04/07/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Design Document | In Progress
2 | SRS Document | In Progress
3 | Product Backlog | In Progress
4 | Coding Convention | Completed
5 | Database | In Progress
6 | Java Project | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Update Menu Bar | GiangNT
2 | Standardize Database Query Style | GiangNT
3 | Update Change Password Feature | GiangNT
4 | Update [Ship] Table in Database | ThongPQ | Add Data
5 | Update [Users] Table in Database | GiangNT | Add Email
6 | Update Product Backlog | GiangNT
7 | Update Slideshow in Compare | HuyenBN | Style
8 | Search Account in Account Manager | ThongPQ
9 | Feedback Feature in Product Detail | HuyenBN | Style
10 | Update Edit Account | ThongPQ | Add Email
11 | Update Account Manager | HuyenBN | Style
12 | Blog Feature | ThongPQ | BlogListControl, BlogDetailControl, BlogDAO
13 | Blog Feature | ThongPQ | Blog Table in Database
14 | Blog Feature | ThongPQ | Blog.jsp, BlogDetail.jsp
15 | Update DashBoard | HuyenBN | Pie Chart, Bar Chart of Recent Order and Style
16 | Create Home Page | GiangNT
17 | Update [Orders] Table in Database | HuyenBN
18 | Update Finish Page | HuyenBN | Design
19 | Feedback Feature | DatTT | Star
20 | Update Order and Order Detail Function | ThuanDT | Add Status
21 | Notification Feature | ThuanDT
22 | Update Invoice Feature | ThuanDT
23 | Update Order Detail Feature | DatTT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Style Pages | 2021-11-07 | HuyenBN
2 | Product Detail of Marketing Feature | 2021-11-07 | HuyenBN
3 | Update Home Page Design | 2021-11-07 | GiangNT
4 | Update Web Skeleton | 2021-11-07 | GiangNT
5 | Update Menu Bar | 2021-11-07 | GiangNT
6 | Update Blog Feature | 2021-11-07 | ThongPQ
7 | Update Sequence Diagram in SRS Document | 2021-11-07 | ThongPQ
8 | Update Feedback Feature | 2021-11-07 | DatTT
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C41: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue