## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration | Status | Detail
Home Page | Public | Complex | Iteration 1 |  |  |  | Đang
Products List | Public | Medium | Iteration 1 |  | Nguyen The Giang
Product Details | Public | Medium | Iteration 1 |  | Nguyen The Giang |  | Còn feedback
Cart Details | Public | Medium | Iteration 1 |  | Nguyen The Giang
Cart Contact (List Cart) | Public | Simple | Iteration 1 |  | Nguyen The Giang
User Login | Common | Simple | Iteration 1 |  | Nguyen The Giang
User Register | Common | Simple | Iteration 1 |  | Nguyen The Giang
User Authorization (gửi mail) | Common | Simple | Iteration 1 |  | Tran Tat Dat
Admin Dashboard | Admin | Simple | Iteration 1 |  | Nguyen The Giang |  | Còn Style
Users List | Admin | Simple | Iteration 1 |  | Nguyen The Giang |  | Còn Paging
User Details | Admin | Simple | Iteration 1 |  |  |  |  | Khi bấm vào 1 User trong List -> hiển thị chi tiết
Cart Completion | Public | Simple | Iteration 2 |  | Nguyen The Giang
Reset Password | Common | Simple | Iteration 2 |  | Nguyen The Giang
Change Password | Common | Simple | Iteration 2 |  | Tran Tat Dat
User Profile | Common | Simple | Iteration 2 |  |  |  | Còn Style
My Orders (xem lịch sử order) (tổng quát) | Customer | Simple | Iteration 2 |  |  |  | Còn Style
Order Information (chi tiết) | Customer | Simple | Iteration 2 |  | Tran Tat Dat, Dinh The Thuan |  | Còn Style
Products List | Marketing | Simple | Iteration 2 |  | Nguyen The Giang |  |  | (Là Manager Product)
Product Details | Marketing | Simple | Iteration 2
Customers List | Marketing | Simple | Iteration 2 |  | Dinh The Thuan |  | Hỏi Thuận: Total Invoices có chưa (nếu chưa có thì thêm 1 trang nữa)
Customer Details | Marketing | Simple | Iteration 2 |  | Dinh The Thuan |  | cx thế
Sale Dashboard | Sale | Simple | Iteration 2 |  | Nguyen The Giang
Orders List | Sale | Simple | Iteration 2 |  | Dinh The Thuan |  | Sửa lại trang Total Invoices
Order Details | Sale | Simple | Iteration 2 |  | Dinh The Thuan |  | Cx thế
Feedback | Public | Simple | Iteration 2
Blogs List | Public | Simple | Iteration 3 |  |  |  |  | Chỉ có Seller Post thôi
Blog Details | Public | Simple | Iteration 3
MKT Dashboard | Marketing | Simple | Iteration 3 |  | Nguyen The Giang
Posts List | Marketing | Simple | Iteration 3 |  |  |  |  | Danh sách các Blog do Seller tạo ra
Post Details | Marketing | Simple | Iteration 3
Sliders List | Marketing | Simple | Iteration 3 |  |  |  | Slot sau hỏi thầy
Slider Details | Marketing | Simple | Iteration 3 |  |  |  | Cx thế
Feedbacks List | Marketing | Simple | Iteration 3
Feedback Details | Marketing | Simple | Iteration 3